## Read Me
Definitions - Different Sheets used in Business Process Review
Products | It demonstrates model bank products being covered in BPR sheet and update bank product list if required
Processes | All Model Bank / Local Processes relevant to bank business are mentioned and discussed with the bank
Scoping Gaps | This sheet contains Gaps, Back to core items – Customization that could be replaced by R21 core features, Existing customizations that will be retrofitted to R19 etc.
Follow Up Sheet | Items require follow up are recorded in this sheet for any action and decision to reflect in scoping gap sheet

## Sign Off
# | Name | Role | Company | Signature | Date
1 | Indrajit Roy Choudhury |  | TBI |  | 2021-12-20
2 | Habib |  | TBI |  | 2021-12-20
3 | Kanwal Deep | Project Director | NDC |  | 2021-12-20

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1 | 1 | Nauman Hussain | 2021-12-20
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Products (hidden)
Product ID | PRODUCT | OVERVIEW | FEATURES | CURRENCY | INTEREST RATE | PA | Start Slippage | Duration Slippage | Process Discussion Status | Comments

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
WS02-LI-TBI | Limit
WS02-LI-TBI-01 | Setup Limit- Limit Reference | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-02 | Global Limit | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-03 | Limit Products Hierarchy | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-04 | Multi level Sub Products | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-05 | Revolving and Non revolving Limits | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
Limit Menu
WS02-LI-TBI-06 | Create Secured Limit | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-07 | Create Unsecured Limit | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-08 | Maintain/Reverse Limit | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-09 | Change Customer Liability | Gap Identified | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-10 | Sub Allocate Limit | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-11 | Authorise/Delete/Reject Limit | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-LI-TBI-12 | Authorise/Delete Limit Sub Allocation | As per MB | 2021-12-20 | 2021-12-20 | 2021-12-20 | 2021-12-20 |  |  | Completed

## Scoping Gaps
Business Process Review Sheet - Limit Management
WS Ref | Description | Process Reference # | Gap Number | Process Name | Contact person | Raised by (Department) | MoSCoW Classification | Gap Category | Gap Type | Requirement Type | Gap Effort | Gap Status | Actions/ Comments | Functional / high Level Solution | Workshop Date | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Dropped In | Dropped Date | NDC Comments
WS02-LI-TBI | Client is requesting to have an automation done when the change customer liability function is performed. The automation is to update the exisiting limits of the new entrant into the group limit structure. System need to check the Goup limit sanction amount and raise an error message if it getting breached with the sanction value of the new entrant. | WS02-LI-TBI-09 | WS02-LI-TBI-09.1 | Change Customer Liability | Indrajit | TBI | Good to have | Bank Requirement | Customization | New Requirement | [5 empty] | TBD |  |  | TBD |  |  | This would be a major development. Presently the system caters this approach manually. As the exisitng limits of the new entrant are dissolved and new limits under the group are created to cater for the existing deal of the customer.

## Followup Sheet (hidden)
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments | Aging | TAT

## Legend (hidden)
Description of Drop Down Fields - Scoping Gap Sheet
Description
| Gap Category | Not Defined Yet | Category is to be identified
|  | Regulatory | As per regulations
|  | Bank Requirement | Specific to bank internal process or User Wishlist
|  | Sharia | It is based on sharia compliant
| Gap Type | Configuration | Can be addressed through enquiry, versions, composite screens etc
|  | Parameterisation | Can be addressed through enquiry, versions, composite screens etc
|  | Customization | Development required
| Requirement Type | Existing - Manual | Currently being addressed as a manual process
|  | Existing - System | Currently it is available in bank existing system
|  | New Requirement | It is a new requirement , can be bank specific, regulatory, sharia etc.
| Gap Effort | Low | 1-3 Days
|  | Medium | 3-10 Days
|  | High | > 10 Days
| Gap Status | Open | Decision to be made
|  | Dropped | Functionality not required
|  | Agreed | Gap has been accepted
|  | Workaround | The Workaround or Standard Model Bank Process has been accepted by the users
Description of Drop Down Fields - Scoping Gap Sheet
| Priority | Low | Does not impact on sign off
|  | Medium | Important but can be addressed in BRD
|  | High | Must be addressed to close and sign off BPR sheet
| Status | Open | Item still under follow up, action to be taken
|  | Closed | Requirement provided, decision has been made
| Responsibility | Client | Client to Respond
|  | NDC | NDC to Respond
|  | Anabatic | Other stakeholder to respond, Like Temenos, 3rd Party client etc
Temenos
| Category | Deliverable
Technical Decision
Business Decision
Need Further discussion
| Process Discussion | Not Yet Started
Completed
Deferred
In Progress
| Level | As per MB
Gap Identified