## Sign Off
# | Name | Role | Company | Signature | Date

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1 | 1 | Taiyyab Azim | 2021-12-22
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Products
Product ID | PRODUCT | OVERVIEW | FEATURES | CURRENCY | INTEREST RATE | PA | Start Slippage | Duration Slippage | Process Discussion Status | Comments
Trade Finance
| Import Letter of Credit | Applicant Must be a Customer | Collect Charges & Commissions. Online Limits, Accounting Updates. SWIFT, Letters and Advices generates on line. | Any ISO standard Currency | NA | NA |  |  | Completed
| Export Letter of Credit | Beneficiary and LC Issuance Bank Must be a Customer | Collect Charges & Commissions. Online Limits, Accounting Updates. SWIFT, Letters and Advices generates on line. | Any ISO standard Currency | NA | NA |  |  | Completed
| Inward Documentary Collection | Applicant Must be a Customer | Collect Charges & Commissions. Online Limits, Accounting Updates. SWIFT, Letters and Advices generates on line. | Any ISO standard Currency | NA | NA |  |  | Completed
| Outward Documentary Collection | Beneficiary and LC Issuance Bank Must be a Customer | Collect Charges & Commissions. Online Limits, Accounting Updates. SWIFT, Letters and Advices generates on line. | Any ISO standard Currency | NA | NA |  |  | Completed
| Inward Clean Collection | Applicant Must be a Customer | Collect Charges & Commissions. Online Limits, Accounting Updates. SWIFT, Letters and Advices generates on line. | Any ISO standard Currency | NA | NA |  |  | Completed
| Outward Clean Collection | Beneficiary and LC Issuance Bank Must be a Customer | Collect Charges & Commissions. Online Limits, Accounting Updates. SWIFT, Letters and Advices generates on line. | Any ISO standard Currency | NA | NA |  |  | Completed
| LC Reimbursement Processing | LC Issuance Bank Must be a Customer | Register/Amend Reimbursment, Aceept / Pay / Reject Claims. Charge Commissions | Any ISO standard Currency | NA | NA |  |  | Completed

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Duration (Hrs) | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
WS04 | TRADE FINANCE
WS04-01 | Letter of Credits
WS04-01-01 | Issuance Import LC
WS04-01-01.1 | Pre Advice of Import LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-01.2 | Pre Advice to Issue/List of Preadvised LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-01.3 | Issue of Sight Payment LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-01.4 | Issue of Usance LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-01.5 | Issue of Negotiation LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-01.6 | Issue of Mixed Payment LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-01.7 | Issue of Stand By LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-01.8 | Issue Internet LCs | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-02 | Maintenance of Import LCs
WS04-01-02.1 | Take/Reduce Margin | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-02.2 | Release Margin | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-02.3 | Internal Amendment | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-02.4 | External Amendment | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-02.5 | Amendment seeking Benef's Consent | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-02.6 | Approve/Reject Amendment of Import LC | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-02.7 | Cancellation of Import LC | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-03 | Import Drawings (Clean)
WS04-01-03.1 | Lodge Documents under Import LC | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-03.2 | Drawings Under Shipping Guarantee | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-03.3 | Sight Payment under Import LC | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-03.4 | Acceptance of Documents | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-03.5 | Online Maturity of Acceptances(Imports) | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-03.6 | Amendment to Paid Drawings | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-04 | Import Drawings (Discrepant)
WS04-01-04.1 | Lodge Documents under Import LC | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-04.2 | Documents Pending for Applicant Approval | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-04.3 | Reject Documents under Import LC | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-04.4 | Handling of Rejected Documents(Imports) | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-04.5 | Online Maturity of Accepted Documents | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-04.6 | Amendment to Paid Documents | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-05 | Import Drawings Released Under Trust | [9 empty] | Financing Related Products Will Be Part Of MVP II
WS04-01-05.1 | Release Document Under Trust
WS04-01-05.2 | Pay/Reject/Accept Doc Released Under Trust
WS04-01-05.3 | Online Maturity of Accepted Documents
WS04-01-05.4 | Final Rejection of Documents
WS04-01-06 | Sight Payment under Import LC (with Finance) | [9 empty] | Financing Related Products Will Be Part Of MVP II
WS04-01-07 | Create Loan for Import Payment | [9 empty] | Financing Related Products Will Be Part Of MVP II
WS04-01-08 | Discounting of Usance Bills(Imports) | [9 empty] | Financing Related Products Will Be Part Of MVP II
WS04-01-09 | Discounting of Usance Bills(Imports)
WS04-01-10 | Amendment to Usance Discounting
Export Letter of Credits
WS04-01-09 | Advice Export LCs
WS04-01-09.1 | Pre-Advice | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.2 | PreAdvice to Advice/List of Preadvised LCs | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.3 | Advise/Register Sight Payment LCs | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.4 | Advise/Register Usance LCs | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.5 | Advise/Register Negotiation LCs | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.6 | Advise/Register Mixed Payment LCs | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.7 | Advise/Register Stand By LCs | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.8 | Inward SWIFT Message (LC) | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-09.9 | Transfer of Export LCs | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-10 | Amend Export LCs
WS04-01-10.1 | Internal Amendment | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-10.2 | External Amendment | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-10.3 | Amendment seeking Benef's Consent | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-10.4 | Approve/Reject Amendment of Export LC | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-10.5 | Cancellation of Export LC | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-11 | Export Drawings (Clean)
WS04-01-11.1 | Lodge Documents under Export LC | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-11.2 | Sight Payment under Export LC | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-11.3 | Acceptance under Export LC | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-11.4 | Online Maturity of Acceptances | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-12 | Export Drawings (Discrepant)
WS04-01-12.1 | Lodge Discrepant Docs under Export LC | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-12.2 | Reject Discrepant Documents (Exports) | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-12.3 | Handling of Rejected Documents(Exports) | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-12.4 | Online Maturity of Acceptance Documents | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-13 | Export Drawings Under Reserve | [9 empty] | Financing Related Products Will Be Part Of MVP II
WS04-01-13.1 | Payment Under Reserve (Exports)
WS04-01-13.2 | Payment of Sight Bill Paid Under Reserve
WS04-01-13.3 | Bill (Paid Under Reserve) Returned Unpaid
WS04-01-13.4 | Final Rejection of Export Bills
WS04-01-14 | Export Drawings Discounted / Negotiation | [9 empty] | Financing Related Products Will Be Part Of MVP II
WS04-01-14.1 | Sight Bill Negotiation / Discounting
WS04-01-14.2 | Amendment to Sight Discouting
WS04-01-14.3 | Usance Bill Negotiation / Discounting
WS04-01-14.4 | Amendment to Usance Negotiation / Discounting
WS04-01-15 | Export Loan and Adjustment from Bill Proceeds | [9 empty] | Financing Related Products Will Be Part Of MVP II
WS04-01-15.1 | Create Export Packing Credit Limit
WS04-01-15.2 | Create Export Packing Credit Account
WS04-01-15.3 | Sight Negotiation-Adjustment of EPC
WS04-01-15.4 | Create Export Packing Credit Loan
WS04-01-15.5 | Sight Negotiation-Adjustment of Loan
.
Inward Collection
WS04-01-16 | Register Import Collection
WS04-01-16.1 | Lodge Sight Documentry Collection | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-16.2 | Lodge Usance (Tenor) Documentary Collection | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-16.3 | Lodge Clean Collection | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-16.4 | Amend Import Collection | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-16.5 | Accept Import Collection | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-16.6 | Payment of Inward Collection | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
WS04-01-16.7 | Close Import Colletion / Non Payment | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20
.
Outward Collection
WS04-01-17 | Register Export Collection
WS04-01-17.1 | Define Direct Collection Range for Customers | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.2 | Lodge Sight Docy Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.3 | Lodge Usance(Tenor) Documentary Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.4 | Lodge Clean Collections | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.5 | Amend Outward Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.6 | Trace the Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.7 | Acceptance of Outward Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.8 | Payment of Outward Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.9 | Settle Purchase Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21
WS04-01-17.10 | Payment of Outward Collection | As Per MB | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21

## Scoping Gaps
WS Ref | Description | Process Reference # | Gap Number | Process Name | Workshop Date | Contact person | Raised by (Department) | MoSCoW Classification | Gap Category | Gap Type | Requirement Type | Gap Effort | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Actions/ Comments | SMB Availability | Functional Classification | Dropped In | Dropped Date
WS04-01 | Separate Margin Account For Each Customer. - Customer.Account Enquiry to show customer non-checking acounts only for provision parking in Credit account | WS04-01-01 to 07 | WS04-01-01.01 | Import LC Issuance | 2021-12-20 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-02 | LCs to be bifurcated into Internal/Inland /LC Swift Option To Be Removed If Both Beneficiary And Applicant Are Bank Customer Then. The LC Types For Internal/Inland LCs Are: Sight LC, Usance LC And Mixed Payment LCs. | WS04-01-01 to 07 WS04-01-09.1 to 9 | WS04-01-01.02 | Import LC Export LC | 2021-12-20 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | High
WS04-03 | Seperate Report/Enquiry For Internal/Inland LCs (Internal LCs) | WS04-01-01 to 07 | WS04-01-01.03 | Import LC Issuance | 2021-12-20 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-04 | Local Field to be Added: *Beneficiary Country Field Required (Under The Beneficiary Field In Parties To LC Tab) | WS04-01-01 to 07 | WS04-01-01.01 | Import LC Issuance | 2021-12-20 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-05 | Enquiry For All Swift/Advices Messages for both; Inward And Outward For Particular Transactions. | WS04-01 | WS04-01-01.04 | Import LC & Drawings Export LC & Drawings Inward Collection Outward Collection | 2021-12-20 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-06 | In Charges Tab "Charge Status Field" Only Charge Status 2: Collected And Charge Status 3: Charges Claimed To Show And Charge Status 15: Waived To Be Removed From The Drop Down Field. | WS04-01 | WS04-01-01.06 | Import LC Export LC Inward Collection Outward Collection | 2021-12-20 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-07 | Local Fields to be added: VESSEL NAME Field Required For Screening Purpose CARRIER COMPANY Field Required For Screening Purpose AGENT Field Required For Screening Purpose MANUFACTURER Field Required For Screening Purpose | WS04-01 | WS04-01-01.09 | Import LC Drawings Export LC Drawings Inward Collection Outward Collection | 2021-12-20 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-08 | Under Export Lodgement schedule; Expiry Date Field to be added | WS04-01-11.1 to 04 WS04-01-12.1 to 04 WS04-01-13.1 to 04 WS04-01-14.1 to 04 | WS04-01-01.12 | Export LC Drawings (Document Capture Stage) | 2021-12-21 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium

## Followup Sheet
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments | Aging | TAT
1 | 2020-12-22 | No Gap setup process | Schedule of Charges | SOC To shared with NDC for the Charges Setup | Medium | Open | Client | Trade Finance
2 | 2020-12-22 | No Gap setup process | LC Documents Codes | Bank to Share the Description Of Goods Codes | Medium | Open | Client | Trade Finance | [6 empty] | 0 | N/A
3 | 2020-12-22 | No Gap setup process | Import LC/Collection | Narrative Required For Advices Available In Debit Advices | Medium | Open | Client | Trade Finance | [6 empty] | #REF! | #REF!
4 | 2020-12-22 | No Gap setup process | Export LC/Collection | Narrative Required For Advices Available In Debit Advices | Medium | Open | Client | Trade Finance | [6 empty] | 0 | N/A
5 | 2020-12-22 | No Gap setup process | LC and MD Modules On All Transaction Stages | Authorization Levels: Input, Review And Authorize. Bank To Confirm | Medium | Open | Client | Trade Finance | [6 empty] | #REF! | #REF!
Formulas:
Aging = IF([Status]="Closed",[Actual End Date]-[Expected End Date],IF([Expected End Date]>TODAY(),0,IF([Expected End Date]="",0,NETWORKDAYS([Expected End Date]+2,TODAY()+2,6)-1)))
Aging = IF(#REF!="Closed",[Actual End Date]-[Expected End Date],IF([Expected End Date]>TODAY(),0,IF([Expected End Date]="",0,NETWORKDAYS([Expected End Date]+2,TODAY()+2,6)-1)))
TAT = IF([Status]="Closed",NETWORKDAYS([Date Raised]+2,[Actual End Date]+2,6)-1,"N/A")
TAT = IF(#REF!="Closed",NETWORKDAYS(#REF!+2,[Actual End Date]+2,6)-1,"N/A")

## Drop Down Fields
MoSCoW | Scoping Gaps | Scoping Gaps | Level
MUST Have | Build IP | Not Defined Yet | As Per MB
SHOULD Have | Delivered | Regulatory | GAP Identified
COULD Have | Other Country Requirement | Bank Requirement | PMB
WON'T Have | Moved to Other Stream | Dropped | GAP Identified PMB
| To be Discussed | PMB
Effort |  | PMB/Bank Requirement | New Gaps
Low | Gap Status |  | Duplicate
Medium | In Progress |  | New Requirement
High | Rejected |  | Moved to Future Release
| Agreed |  | Details Required
Type |  |  | Dropped
Not Defined Yet |  | Gap Priority | Moved to Other Stream
Configuration | Process Status | High | To be Discussed
Parameterisation | Not Started | Medium | Features List Requirement
Customization | In Progress | Low | BSD Required
Core | Completed |  | BSD Delivered
Add of LOVs | Deffered | FSD Status | Change Request
Category (Follow Up) |  | FSD Under Development | Item Status
Deliverables | Follow Up Status | FSD Review 1 | Critical
Tech Decision | Open | FSD Review 2 | Needs Attention
Business Decision | Closed | FSD Review 3 | On Track
Extra Discussion |  | Pending Sign-off
| BRD Status | Signed-off
Owner | BRD Under Development |  | Priority
Client | BRD Review | Workshop Attendance | Priority 1
NDC | Pending Sign-off | N/A | Priority 2
| Signed-off | Yes | Priority 3
| Dropped by Bank | No
RAG Status
On Track
Needs Attention
Critical