## Sign Off
# | Name | Role | Company | Signature | Date

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1 | 1 | Taiyyab Azim | 2021-12-22
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Products
Product ID | PRODUCT | OVERVIEW | FEATURES | CURRENCY | INTEREST RATE | PA | Start Slippage | Duration Slippage | Process Discussion Status | Comments
Guarantees | Guarantee Issued | Different type of Guarantees can issue on behalf of Cusomer | Can be live till original instrument receive. Charges & Commission can be Collect date wise. SWIFT/Letters/Advices generates. | Any ISO standard Currency | NA | NA | NA | NA | Completed
Guarantees | Multi Participants Guarantees | Multi Participants Guarantees can be issued | Can be live till original instrument receive. Charges & Commission can be Collect date wise. SWIFT/Letters/Advices generates. | Any ISO standard Currency | NA | NA | NA | NA | Completed
Guarantees | Guarantees Received | Issuing, and advising of guarantee to the Beneficiary for the Guarantee Received | Can be live till original instrument receive. Charges & Commission can be Collect date wise. SWIFT/Letters/Advices generates. | Any ISO standard Currency | NA | NA | NA | NA | Completed

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Duration (Hrs) | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
WS04 | TRADE FINANCE
WS04-MD | Guarantees
Issue of Guarantee
WS04-MD-01 | Issue of Generic Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-02 | Issue of Bid Bonds | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-03 | Issue of Performance Bond | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-04 | Issue of Stand LC | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-05 | Issue of Shipping Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-06 | Issue of Shipping Guarantee Against Collection | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-07 | Issue of Multiparticipant Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
Maintenance Of Guarantees
WS04-MD-08 | Amendment of Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-09 | Change Commission Rate | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-10 | Release Guarantee Margin | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-11 | Register Claim under Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-12 | Pay/ Reject Claim under Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-13 | Expiry of Guarantees | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-14 | Cancellation of Shipping Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-15 | Reinstate Liquidated Guarantees | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
External Asset Register
WS04-MD-16 | Real Estate Register | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-17 | Art and Antiques Register | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
Guarantee Received
WS04-MD-18 | Guarantee Received Generic | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-19 | Guarantee Received Covering Facility | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-20 | Amendment to Guarantee Received | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-21 | Inward Guarantees Received | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
Commission and Charges Processing
WS04-MD-22 | Guarantee Claimed Commission Settlement | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-23 | Guarantee Commission Refund | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-24 | Writeoff of Uncollected Commission | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-25 | Refund of Guarantee Charges | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
Unauthorised Guarantee Transaction
WS04-MD-26 | Unauthorised Guarantee Transactions | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
Authorise/Delete Guarantee Transaction
WS04-MD-27 | Authorise/Delete Guarantee Issued | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-28 | Authorise/Delete Guarantee Received | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-29 | Authorise/Delete Comm Rate Change | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-30 | Authorisation of Guarantee Comm Transactions | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-31 | Authorisation Refund of Charges | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
Enquiries
WS04-MD-32 | Bank Guarantees Issued Outstanding | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-33 | Bank Guarantees Received Outstanding | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-34 | Oustanding Shipping Guarantees | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-35 | Guarantees Due for Expiry | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-36 | Guarantees Expired but not Liquidated | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-37 | Invocation Claims Received Under Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-38 | Invocation Claims Paid under Guarantee | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22
WS04-MD-39 | Reversed MD Deals | As per MB | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22

## Scoping Gaps
WS Ref | Description | Process Reference # | Gap Number | Process Name | Workshop Date | Contact person | Raised by (Department) | MoSCoW Classification | Gap Category | Gap Type | Requirement Type | Gap Effort | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Actions/ Comments | SMB Availibility | Functional Classification | Dropped In | Dropped Date
WS04-MD-01 | New Product to be added *Warranty Guarantee | WS04-MD-01 TO 07 | WS04-MD-01 TO 07.01 | Issue of Guarantee | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-MD-02 | Field to be added in GTEE Issance version; Beneficiary Country (Free Text Field) Counter-Guarantee Reference (Enquiry to reflect all GTEE Received) The same Fields To Be Reflect In The Report - GTEE Outstanding | WS04-MD-01 TO 07 | WS04-MD-01 TO 07.02 | Issue of Guarantee | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-MD-03 | Local Field to be Added on GTEE Received Type of GTEE (Free Text Field) Issuer's Country Field (Free Text Field) | WS04-MD-18 TO 21 | WS04-MD-18 TO 21.01 | Guarantee Received | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-MD-04 | Field to be added in GTEE Received/Claim Register version; Beneficiary Name To Be Changed To Applicant. Applicant Country (Free Text Field) | WS04-MD-18 TO 21 | WS04-MD-18 TO 21.02 | Guarantee Received Claim Register Under Guarantee Received | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-MD-05 | Guarantee Issued Should Give Error Message When Expiry Date And Amount Are Exceeding The Counter Received Guarantee Expiry Date And Amount. | WS04-MD-01 TO 07 WS04-MD-18 TO 21 | WS04-MD-18 TO 21.02 | Issue of Guarantee / Guarantee Received | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Customization | New Requirement | Medium
WS04-MD-06 | In Guarantee Issued And Received Outstanding Report The Below Mentioned Field Need To Be Incorporated: CHARGE.DATE CHARGE.CURR CHARGE.CODE CHARGE.AMOUNT | WS04-MD-32 WS04-MD-33 | WS04-MD-32.01 WS04-MD-33.01 | Guarantee Issued Outstanding Report Guarantee Received Outstanding Report | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-MD-07 | At Invocation Claim Version; Add version Of MT-799 | WS04-MD-12 | WS04-MD-12.01 | Pay/Reject Claim under Guarantee | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-MD-08 | Under GTEE Recived Issuance Version: MT799 Associated Versions to be added on version. | WS04-MD-18 TO 21 | WS04-MD-18 TO 21.03 | Guarantee Received | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium
WS04-MD-09 | Under Guarantee Received Charges: Accounting Entry For Claimed Charges Debit Suspense And Credit P/L Then Settle The Entry After Funds Are Received In Nostro Account Nostro A/C Debit And Suspense Account Credit. (Settlment will be done manually by user by Fund Transfer) | WS04-MD-18 TO 21 | WS04-MD-18 TO 21.02 | Guarantee Received | 2021-12-22 | Ahmed Adnan | Trade Finance |  | Bank Requirement | Configuration | New Requirement | Medium

## Followup Sheet
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments
1 | 2020-12-22 | No Gap setup process | Schedule of Charges | SOC will be shared by the client with NDC | Medium | Open | Client
2 | 2020-12-22 | No Gap setup process | Issuance / Amendment Of Guarantee | Excess Over Limit Exceed Convert To Error From Override. Bank To Confirm Since This Is System Wide Setup. | Medium | Open | Client
3 | 2020-12-22 | No Gap setup process | Issuance / Amendment Of Guarantee | Excess Over Limit Exceed Override To Be Authorized By Credit Department And Not The Trade Finance User. User Details To Be Provided By The Bank So That Override Class Can Be Placed In The User Profile Accordingly. | Medium | Open | Client
4 | 2020-12-22 | WS04-MD-33 | Guarantee Received Enquiry | Guarantees Received Report/Enquiry Field Required For 45L Underlying Transaction Details As Per New Swift 2021 Standards. This Field Is Required In The Report/Enquiry. This can be possible upon updation of Swift 2021 setup on the environment. | Medium | Open | Client
5 | 2020-12-22 | No Gap setup process | Swift 2021 | Swift 2021 Standards Update Required For Guarantee Swift Messages | Medium | Open | Client
6 | 2020-12-22 | No Gap setup process | Issuance / Amendment Of Guarantee | Bank To Share Standard Text Which Will Be Incorporated Under MD.CLAUSES | Medium | Open | Client
7

## Drop Down Fields
MoSCoW | Scoping Gaps | Scoping Gaps | Level
MUST Have | Build IP | Not Defined Yet | As Per MB
SHOULD Have | Delivered | Regulatory | GAP Identified
COULD Have | Other Country Requirement | Bank Requirement | PMB
WON'T Have | Moved to Other Stream | Dropped | GAP Identified PMB
| To be Discussed | PMB
Effort |  | PMB/Bank Requirement | New Gaps
Low | Gap Status |  | Duplicate
Medium | In Progress |  | New Requirement
High | Rejected |  | Moved to Future Release
| Agreed |  | Details Required
Type |  |  | Dropped
Not Defined Yet |  | Gap Priority | Moved to Other Stream
Configuration | Process Status | High | To be Discussed
Parameterisation | Not Started | Medium | Features List Requirement
Customization | In Progress | Low | BSD Required
Core | Completed |  | BSD Delivered
Add of LOVs | Deffered | FSD Status | Change Request
Category (Follow Up) |  | FSD Under Development | Item Status
Deliverables | Follow Up Status | FSD Review 1 | Critical
Tech Decision | Open | FSD Review 2 | Needs Attention
Business Decision | Closed | FSD Review 3 | On Track
Extra Discussion |  | Pending Sign-off
| BRD Status | Signed-off
Owner | BRD Under Development |  | Priority
Client | BRD Review | Workshop Attendance | Priority 1
NDC | Pending Sign-off | N/A | Priority 2
| Signed-off | Yes | Priority 3
| Dropped by Bank | No
RAG Status
On Track
Needs Attention
Critical