## Read Me
Definitions - Different Sheets used in Business Process Review
Products | It demonstrates model bank products being covered in BPR sheet and update bank product list if required
Processes | All Model Bank Processes relevant to bank business are mentioned and discussed with the bank
Product Conditions | For designing AA Account product is required their features
Scoping Gaps | This sheet contains Gaps, Back to core items – Customization that could be replaced by R20 core features, Existing customizations that will be retrofitted to R21 etc.
Follow Up Sheet | Items require follow up are recorded in this sheet for any action and decision to reflect in scoping gap sheet

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1 | 1 | Muhammad Kashif | 2021-12-20
2 | 1.1
3 | 1.2
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Sign Off
FIT & GAP APPROVAL SHEET
AA Accounts
# | Name | Role | Company | Signature | Date
Trade Bank of Iraq

## Products
PRODUCT LINE | PRODUCT GROUP | PRODUCTS
ACCOUNT | CURRENT ACCOUNT | TBI Corporate Current Account
TBI Individual Current Account
TBI Staff Current Account
| SAVINGS ACCOUNT | N/A

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Duration (Hrs) | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
WS02-AR | CURRENT & SAVINGS ACCOUNT
Product Catalog AA Accounts
WS02-AR-01 | Open Current Account | GAP Identified | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-AR-03 | Amend Current Account | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-AR-05 | Posting Restriction on Account | As Per MB | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-AR-06 | Generate Account Statement | GAP Identified | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-AR-07 | Account Dormancy | GAP Identified | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20 |  |  | Completed
WS02-AR-08 | Account Enquiry | GAP Identified | 2021-12-20 | 2021-12-20 |  | 2021-12-20 | 2021-12-20 |  |  | Completed

## Scoping Gaps
Business Process Review Sheet - AA Accounts
WS Ref | Description | Process Reference # | Gap Number | Process Name | Contact person | Raised by (Department) | MoSCoW Classification | Gap Category | Gap Type | Requirement Type | Gap Effort | Gap Status | Actions/ Comments | Functional / High Level Solution | Workshop Date | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Dropped In | Dropped Date | NDC Comments | Enquiry/SMS/Email/Report
WS02-AR | Current Corporate Account Currency, SAR, EUR, USD, IQD, GBP, JPY & CNY. | WS02-AR-01 | WS02-AR-01.01 | Open Current Account | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Configuration | New Requirement | High | Open |  | Corporate Current Account will be opened in these Currency SAR, EUR, USD, IQD, GBP, JPY & CNY. | 2021-12-20
WS02-AR | Current Individual & Staff Account Currency, SAR, USD & IQD. | WS02-AR-01 | WS02-AR-01.02 | Open Current Account | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Configuration | New Requirement | High | Open |  | Current Individual & Staff Account will be opened in these Currency, SAR, USD & IQD. | 2021-12-20
WS02-AR | Account length will be 10 as per model bank. | WS02-AR-01 | WS02-AR-01.03 | Open Current Account | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Configuration | New Requirement | Low | Open |  | Account length will be set as "10" in T24. | 2021-12-20
WS02-AR | Iban is required and bank will share the document. | WS02-AR-01 | WS02-AR-01.04 | Open Current Account | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Configuration | New Requirement | Low | Open | Bank will share the IBAN document |  | 2021-12-20
WS02-AR | Mode of Operation bank is required as "Others". | WS02-AR-01 | WS02-AR-01.05 | Open Current Account | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Configuration | New Requirement | Low | Open |  | In account product condition Mode of Operation field will be add more option as "Others". | 2021-12-20
WS02-AR | Dormancy Status, Dormant (2Y), Unclaimed (5Y) & Abandoned (10Y). | WS02-AR-07 | WS02-AR-07.01 | Account Dormancy | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Configuration | New Requirement | Low | Open |  | Dormancy condition will be created as "Dormant (2Y), Unclaimed (5Y) & Abandoned (10Y)". | 2021-12-20
WS02-AR | If new account is opened and no debit and credit transaction happened in this account then after 90 days it will be closed automatically. Regulatory requirement. | WS02-AR-01 | WS02-AR-01.06 | Open Current Account | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Regulatory | Customization | New Requirement | Medium | Open |  | New screen will be designed for Automatic account closing. | 2021-12-20
WS02-AR | Bank is required report those new account where no debit and credit after 90 days close automatically and report will be generated before 10 days means(80 days) past. | WS02-AR-08 | WS02-AR-01.08 | Account Enquiry | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Customization | New Requirement | Medium | Open |  | Enquiry will be designed for Automatic account closing. | 2021-12-20
WS02-AR | No AA Account Statement condition will be use. | WS02-AR-06 | WS02-AR-06.01 | Generate Account Statement | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Configuration | New Requirement | Low | Open |  |  | 2021-12-20
WS02-AR | Bank will share the online (Adhoc) Account statement format. | WS02-AR-01 | WS02-AR-06.02 | Generate Account Statement | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Customization | New Requirement | High | Open | Bank will share the Account Statement Formate. |  | 2021-12-20
WS02-AR | Bank will share the periodic statement format. | WS02-AR-01 | WS02-AR-06.03 | Generate Account Statement | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Customization | New Requirement | High | Open | Bank will share the Account Statement Formate. |  | 2021-12-20
WS02-AR | Basis on customer email id, every month on 2nd day account statement will be generated and it will be sent on customer email automatically. | WS02-AR-01 | WS02-AR-06.04 | Generate Account Statement | Khalid & Muhammad Krimly | Retail Operation Team | SHOULD Have | Bank Requirement | Customization | New Requirement | High | Open |  | AA Account Statement Condition will be used for this requirement. | 2021-12-20
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR
WS02-AR

## Product Conditions
Mandatory Information
Mandatory for Product Configuration
[20 empty] | Dependent on Product Type | [8 empty] | Dependent on Product Type | [31 empty] | Mandatory only in case of charges present in the product
PRODUCT STRUCTURE |  |  |  | ACCOUNT | [6 empty] | OFFICERS |  |  |  | LIMIT |  |  |  |  | CREDIT INTEREST | [8 empty] | DEBIT INTEREST | [8 empty] | TERM.AMOUNT |  |  |  | PAYMENT SCHEDULE |  |  |  |  | CLOSURE | [5 empty] | ELIGIBILITY | [7 empty] | CHARGE | [10 empty] | SETTLEMENT |  |  |  |  | ACTIVITY.RESTRICTION
Sr. No. | Product Group | Product Level | Currency | Category | Account Title | Generate IBAN | Date Convention | Inactive Months | Arr Link | Input Type | Primary Officer | Other Officer - Role | Arr Link | Input Type | Default Limit Reference | Single Limit Y/N | Allow Netting | Arr Link | Input Type | Day Basis | Interest Calculated on | Calculation Source | Accrual Rule | Fixed Rate | Variable Rate | PL category | Arr Link | Input Type | Day Basis | Interest Calculated on | Fixed Rate | Variable Rate | Compounding | Accrual Rule | PL Category | Arr Link | Input Type | Cancel Period | Cooling Period | Pre-Closure Charges | Negotiation rules | Repayment Type | Repayment Method | Repayment Frequency | Arr Link | Input Type | Closure Type | Closure Period | Closure Method | Posting Restriction | Arr Link | Input Type | Eligibility Rules | On online validation failure Produce Error / Override | On Review Failure Ignore / Change Product | Perform Review on Customer Static Changes | Perform Periodic Review / Frequency | If not Eligible change to this product | Arr Link | Input Type | Charge Name | Description | Charge Type | Fixed Amount | Charge calculated on (if variable) | Fee range for variable | Schedule (Frequency) | Activity Based | PL category | Arr Link | Input Type | Payin Rule | Payin Definition | Payout Definition | Arr Link | Input Type | Periodic Attribute | Activity | Arr Link | Input Type
Below two products are sample records.
1 | CURRENT ACCOUNTS | Parent | PKR | [9 empty] | Non Tracking | Negotiable | N/A | [8 empty] | N/A | [6 empty] | N/A | [10 empty] | N/A |  |  |  |  | Balance | 1D | Automatic | 90 | Tracking | Negotiable | [20 empty] | N/A | N/A
|  | Child | PKR | 1002 | AUTO | Yes | backward | 12 | Non Tracking | Negotiable | [42 empty] | CUTOMER.IS.DECEASED | ERROR | IGNORE | YES | 1Y | N/A | Tracking | Non negotiable | [16 empty] | MINIMUM.INITIAL.BALANCE, PKMB.TOTAL.AMT.OF.TXN.ALLOWED, MAXIMUM.BALANCE | ACCOUNTS-LCYCASHDEP-ARRANGEMENT, ACCOUNTS-LCYCASHDRAW-ARRANGEMENT | Tracking | Non negotiable
[53 empty] | KB.CUS.FR | ERROR | IGNORE | YES | 1Y | N/A | Tracking | Non negotiable
[53 empty] | KB.MAN.RISK | ERROR | IGNORE | YES | 1Y | N/A | Tracking | Non negotiable
2 | SAVING ACCOUNTS | Parent | PKR | [43 empty] | Balance |  | Automatic | 90 | Tracking | Negotiable | [8 empty] | SMSCHARGE |  | Calculated |  | 0 |  |  |  | 52534 | Custom Tracking | Negotiable
|  | Child | PKR | 6006 |  | Yes | calendar | 12 | Non Tracking | Negotiable | 1 | 200 | Non Tracking | Negotiable | N/A |  |  |  |  | C 366/366 | CURRBALANCE | CR.AVERAGE | First | 3.75 |  | 50001 | Custom Tracking | Negotiable |  |  | N/A | [10 empty] | INTEREST | Capitalise | 1M,DAY 01 | Non Tracking | Non negotiable |  | N/A |  |  |  |  | CUTOMER.IS.DECEASED | ERROR | IGNORE | YES | 1Y | N/A | Tracking | Non negotiable | MINBALFEE |  | Fixed | 0 |  |  |  |  | 52255 | Tracking | Non negotiable |  | N/A | N/A |  |  | MINIMUM.INITIAL.BALANCE, PKMB.TOTAL.AMT.OF.TXN.ALLOWED, MAXIMUM.BALANCE | ACCOUNTS-LCYCASHDEP-ARRANGEMENT, ACCOUNTS-LCYCASHDRAW-ARRANGEMENT | Tracking | Non negotiable
[53 empty] | KB.CUS.FR | ERROR | IGNORE | YES | 1Y | N/A | Tracking | Non negotiable
Trade Bank of Iraq AA Accounts Prouct Configuration Details
1 | CURRENT ACCOUNTS | Parent |  | NBPSA.CUR.AC.PAR (Same copy of Parent Current Account will be created for TBI. | Same product feature will be used of KSA existing Current Account Product and after the product design BPR changes will be applied on TBI Porduct.
1.1 | TBI Corporate Current Account | Child | SAR, EUR, USD, IQD, GBP, JPY & CNY | NBPSA.CCORP (Same copy of Corporate Current Account will be created for TBI. | Same product feature will be used of KSA existing Current Account Product and after the product design BPR changes will be applied on TBI Porduct.
1.2 | TBI Individual Current Account | Child | SAR, USD & IQD | NBPSA.CIA (Same copy of Individual Current Account will be created for TBI. | Same product feature will be used of KSA existing Current Account Product and after the product design BPR changes will be applied on TBI Porduct.
1.3 | TBI Staff Current Account | Child | SAR, USD & IQD | NBPSA.CSA (Same copy of Staff Current Account will be created for TBI. | Same product feature will be used of KSA existing Current Account Product and after the product design BPR changes will be applied on TBI Porduct.

## Followup Sheet
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments | Aging | TAT
1
2
3
4
5
6
7
8
9
10
11
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Aging = IF([Status]="Closed",[Actual End Date]-[Expected End Date],IF([Expected End Date]>TODAY(),0,IF([Expected End Date]="",0,NETWORKDAYS([Expected End Date]+2,TODAY()+2,6)-1)))

## Legend (hidden)
Description of Drop Down Fields - Scoping Gap Sheet
Description
| Gap Category | Regulatory | As per regulations
|  | Bank Requirement | Specific to bank internal process or User Wishlist
| Gap Type | Retrofitted/Taken over as such into R21 | Existing development moved to new release
|  | Configuration | Can be addressed through enquiry, versions, composite screens etc
|  | Parameterisation | Can be done at TAABS Level, through any local template
|  | Customization | Development required
| Requirement Type | Existing - Manual | Currently being addressed as a manual process
|  | Existing - System | Currently it is available in bank existing system
|  | New Requirement | It is a new requirement , can be bank specific, regulatory, sharia etc.
| Gap Effort | Low | 1-3 Days
|  | Medium | 3-10 Days
|  | High | > 10 Days
| Gap Status | Open | Decision to be made
|  | Dropped | Functionality not required
|  | Agreed | Gap has been accepted
|  | Workaround | The Workaround or Standard Model Bank Process has been accepted by the users
Description of Drop Down Fields - Scoping Gap Sheet
| Priority | Low | Does not impact on sign off
|  | Medium | Important but can be addressed in BRD
|  | High | Must be addressed to close and sign off BPR sheet
| Status | Open | Item still under follow up, action to be taken
|  | Closed | Requirement provided, decision has been made
| Responsibility | Client | Client to Respond
|  | NDC | NDC to Respond
|  | TBI | Other stakeholder to respond, Like Temenos, 3rd Party client etc
Temenos
| Category | Deliverable
Technical Decision
Business Decision
Need Further discussion
| Level | As Per MB
GAP Identified
| Process Discussion Started | Not Started
In Progress
Completed
Deffered
| Input Type | Negotiable
Non negotiable
| ACCRUAL RULES | Both
First
Last

## Drop Down Fields (hidden)
MoSCoW | Scoping Gaps | Scoping Gaps | Level
MUST Have | Build IP | Not Defined Yet | As Per MB
SHOULD Have | Delivered | Regulatory | GAP Identified
COULD Have | Other Country Requirement | Bank Requirement
WON'T Have | Moved to Other Stream | Dropped
To be Discussed
Effort |  |  | New Gaps
Low | Gap Status |  | Duplicate
Medium | In Progress |  | New Requirement
High | Rejected |  | Moved to Future Release
| Agreed |  | Details Required
Type |  |  | Dropped
Retrofitted/Taken over as such into R19 |  | Gap Priority | Moved to Other Stream
Configuration | Process Status | High | To be Discussed
Parameterisation | Not Started | Medium | Features List Requirement
Customization | In Progress | Low | BSD Required
Category (Follow Up) | Completed |  | BSD Delivered
Deliverables | Deffered | FSD Status | Change Request
Tech Decision |  | FSD Under Development | Item Status
Business Decision | Follow Up Status | FSD Review 1 | Critical
Extra Discussion | Open | FSD Review 2 | Needs Attention
| Closed | FSD Review 3 | On Track
Owner |  | Pending Sign-off
Client | BRD Status | Signed-off
NDC | BRD Under Development |  | Priority
| BRD Review | Workshop Attendance | Priority 1
| Pending Sign-off | N/A | Priority 2
Base DateType | Signed-off | Yes | Priority 3
Agreement | Dropped by Bank | No
Start |  |  | RAG Status
| Product Level | Date Convention | On Track
Account Input Type | Parent | forward | Needs Attention
Negotiable | Child | backward | Critical
Non Negotiable |  | calendar
| Single Limit | forward same month | Closure Method
Accrual Rule | Yes |  | None
Both | No | Interest Day Basis | Automatic
First |  | E 366/365 | Manual
Insurance | Closure Type | E1 365/365
Last | None
| Balance | Charge Type | Arr Link
Payin Rule | Maturity | Fixed | Tracking
Full |  | Calculated | Non Tracking
Partial |  |  | Custom Tracking
None |  | Interest Day Basis
A1 360/360
A2 30/360
A3 30/360
A4 30/360
B 366/360
C 366/366
C2 366/366
D 360/366
E 366/365
E1 365/365
F 360/365
F1 360/365
F2 30/365
G 366/364
H 30/356
S SPECIAL
W 252/252
W1 21/252