## Read Me
Definitions - Different Sheets used in Business Process Review
Products | It demonstrates model bank products being covered in BPR sheet and update bank product list if required
Processes | All Model Bank Processes relevant to bank business are mentioned and discussed with the bank
Scoping Gaps | This sheet contains Gaps, Back to core items – Customization that could be replaced by R20 core features, Existing customizations that will be retrofitted to R20 etc.
Follow Up Sheet | Items require follow up are recorded in this sheet for any action and decision to reflect in scoping gap sheet

## Sign Off
FIT & GAP APPROVAL SHEET
TELLER
# | Name | Role | Company | Signature | Date

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1 | 1 | salman & Rana | 2021-01-11
2
3
4
5
6
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Products
Product ID | PRODUCT | OVERVIEW | FEATURES | CURRENCY | INTEREST RATE | PA | Start Slippage | Duration Slippage | Process Discussion Status | Comments
Teller | Teller | The Module handle all cash based management. | This module supports all the Cash based transactions including withdrwal and deposits, till to till transfer and till to vault trasfer. | PKR |  |  |  |  | Completed
Guarantees
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Start Slippage = IF([INTEREST RATE]="","",IF([FEATURES]<[INTEREST RATE],NETWORKDAYS([FEATURES]+2,[INTEREST RATE]+2,6)-1,0))
Duration Slippage = IF([PA]="","",IF([CURRENCY]<[PA],NETWORKDAYS([CURRENCY]+2,[PA]+2,6)-1,0))

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Duration (Hrs) | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
WS02-TT | TELLER
HEAD TELLER OPERATIONS
Till Administration
WS02-TT-01 | Create New Till | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-02 | Change Till User | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-03 | Reopen Teller | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-04 | Authorise/Delete Till Closure | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-05 | Authorise/Delete Till Transfer | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
Cash Management
WS02-TT-06 | Process Cash to Vault | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-07 | Process Cash from Vault | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-08 | Process Cash to Vault - Foreign Ccy | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-09 | Process Cash from Vault - Foreign Ccy | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
TELLER OPERATIONS
Teller Cash
WS02-TT-10 | Cash deposit Local | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-11 | Cash withdrawal Local | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-12 | Cash withdrawal Local (Without Cheque) | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-13 | Cash Deposit Local - Foreign | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-14 | Cash withdrawal Local- Foreign | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-15 | Change Denomination | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-16 | Cash deposit Foreign | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-17 | Cash withdrawal Foreign | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-18 | Authorise/Delete Teller Cash Transactions | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-19 |  | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
Currency Exchange
WS02-TT-24 | Sell Fgn Ccy against Local Ccy | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-25 | Buy Fgn Ccy against Local Ccy | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-26 | Foreign Currency Exchange | GAP Identified | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-27 | Authorise/Delete Currency Exchange | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-28 | Exchange Rates | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
Completed
Account Transfer
WS02-TT-29 | Account to Account Transfer | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-30 | Authorise/Delete Account Transfer | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
Till Transfer
WS02-TT-31 | LCY Till Transfer | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-32 | FCY Till Transfer | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-33 | Till to Vault | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-34 | Vault to Till | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06
WS02-TT-35 | Initiate Till Closure | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
Enquiries
WS02-TT-36 | Cash Position by Till | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-37 | Cash Position by Currency | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-38 | Cash Position by Denomination | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-39 | TC Stock Position by Currency | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-40 | Local Draft Enquiries | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-41 | Till Cash Entries Today | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-42 | Till TC Issue Entries Today | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-43 | Till TC Buy Entries Today | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-44 | Account Balances | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-45 | Reversed Teller Transactions | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
WS02-TT-46 |  | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed
Reversal Today Teller Txn
WS02-TT-47 | Teller Rev Txn | As Per SMB | 2022-01-06 | 2022-01-06 |  | 2022-01-06 | 2022-01-06 |  |  | Completed

## Scoping Gaps
WS Ref | Description | Process Reference # | Gap Number | Process Name | Contact person | Raised by (Department) | MoSCoW Classification | Gap Category | Gap Type | Requirement Type | Gap Effort | Gap Status | Actions/ Comments | Functional / High Level Solution | Workshop Date | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Dropped In | Dropped Date | NDC Comments | Enquiry/SMS/Email/Report
WS02-TT | 1.When user will input Depositor Legal ID No in TELLER,NBPSA.LCY.CASHIN “NBPSA.ID.REF.NO” Field if that legal id is belong to existing customer then fetch detail from system and auto populate the below fields otherwise make it blank for inputting. • Depositor Legal ID Type • Depositor Legal ID No • Depositor Name • Despositor ID Expiry Date • Mobile Number | WS02-TT-10 | WS02-TT-10.01 | Cash deposit Local |  |  | MUST Have | Bank Requirement | Customization | New Requirement | Medium | Agreed
WS02-TT | 1. When user will input withdrawer Legal ID No in TELLER,NBPSA.LCY.CASHCHQ “NBPSA.ID.REF.NO” Field if that legal id is belong to existing customer then fetch detail from system and auto populate the below fields otherwise make it blank for inputting. • Withdrawer Legal ID Type • Withdrawer Legal ID No • Withdrawal Name • Mobile Number • Withdrawer ID Expiry Date | WS02-TT-11 | WS02-TT-11.1 | Cash withdrawal Local |  |  | MUST Have | Bank Requirement | Configuration | New Requirement | Medium | Agreed
WS02-TT | 1. When user will input withdrawer Legal ID No in TELLER, NBPSA.LCY.CASHWDL “NBPSA.ID.REF.NO” Field if that legal id is belong to existing customer then fetch detail from system and auto populate the below fields otherwise make it blank for inputting. • Withdrawer Legal ID Type • Withdrawer Legal ID No • Withdrawer Name • Mobile Number • Withdrawal ID Expiry Date | WS02-TT-12 | WS02-TT-12.1 | Cash withdrawal Local (Without Cheque) |  |  | MUST Have | Bank Requirement | Configuration | New Requirement | Low | Agreed
WS02-TT | 1. When user will input Depositor Legal ID No in TELLER,NBPSA.LCY.CASHIN.FCY.ACCT “NBPSA.ID.REF.NO” Field if that legal id is belong to existing customer then fetch detail from system and auto populate the below fields otherwise make it blank for inputting. • Depositor Legal ID Type • Depositor Legal ID No • Depositor Name • Mobile Number • Deposite ID Expiry Date | WS02-TT-13 | WS02-TT-13.1 | Cash Deposit Local - Foreign |  |  | MUST Have | Bank Requirement | Configuration | New Requirement |  | Agreed
WS02-TT | 1. When user will input withdrawer Legal ID No in TELLER,NBPSA.LCY.CASHCHQ.FCY.ACCT “NBPSA.ID.REF.NO” Field if that legal id is belong to existing customer then fetch detail from system and auto populate the below fields otherwise make it blank for inputting. • Withdrawer Legal ID Type • Withdrawer Legal ID No • Withdrawer Name • Withdrawer ID Expiry Date | WS02-TT-14 | WS02-TT-14.1 | Cash withdrawal Local- Foreign |  |  | MUST Have | Bank Requirement | Configuration | New Requirement | Low | Agreed
WS02-TT | 1.When user will input Depositor Legal ID No in TELLER,NBPSA.FCY.CASHIN “NBPSA.ID.REF.NO” Field if that legal id is belong to existing customer then fetch detail from system and auto populate the below fields otherwise make it blank for inputting. • Depositor Legal ID Type (Dropdown) • Depositor Legal ID No • Depositor Name • Depositor ID Expiry Date • Mobile Number | WS02-TT-16 | WS02-TT-16.1 | Cash deposit Foreign |  |  |  | Bank Requirement | Configuration | New Requirement | Medium | Agreed
WS02-TT | 1. When user will input withdrawer Legal ID No in TELLER,NBPSA.FCY.CASHCHQ “NBPSA.ID.REF.NO” Field if that legal id is belong to existing customer then fetch detail from system and auto populate the below fields otherwise make it blank for inputting. • Withdrawal Legal ID Type • Withdrawal Legal ID No • Withdrawer Name • Withdrawer ID Expiry Date • Mobile Number | WS02-TT-17 | WS02-TT-17.1 | Cash withdrawal Foreign |  |  |  | Bank Requirement | Configuration | New Requirement | Medium | Agreed
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT
WS02-TT

## Followup Sheet
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments | Aging | TAT
1 |  | WS02-TT-10 | WS02-TT-11.01 | cheque scanner machine to process cheques without any problems. cheque reader machine is a tool that scans the front and back of the cheque and sends their digital images to a computer program for processing so that process is belongs to third party which is not belongs to T24 | Low |  | Client

## Legend
Description of Drop Down Fields - Scoping Gap Sheet
Description
| Gap Category | PKMB | Pakistan Model Bank
|  | Regulatory | As per regulations
|  | Bank Requirement | Specific to bank internal process or User Wishlist
|  | Sharia | It is based on sharia compliant
| Gap Type | Configuration | Can be addressed through enquiry, versions, composite screens etc
|  | Parameterisation | Can be addressed through enquiry, versions, composite screens etc
|  | Customization | Development required
| MoSCoW | MUST Have
SHOULD Have
COULD Have
WON'T Have
| Requirement Type | Existing - Manual | Currently being addressed as a manual process
|  | Existing - System | Currently it is available in bank existing system
|  | New Requirement | It is a new requirement , can be bank specific, regulatory, sharia etc.
| Gap Effort | Low | 1-3 Days
|  | Medium | 3-10 Days
|  | High | > 10 Days
| Gap Status | Open | Decision to be made
|  | Dropped | Functionality not required
|  | Agreed | Gap has been accepted
|  | Workaround | The Workaround or Standard Model Bank Process has been accepted by the users
Description of Drop Down Fields - Scoping Gap Sheet
| Priority | Low | Does not impact on sign off
|  | Medium | Important but can be addressed in BRD
|  | High | Must be addressed to close and sign off BPR sheet
| Status | Open | Item still under follow up, action to be taken
|  | Closed | Requirement provided, decision has been made
| Responsibility | Client | Client to Respond
|  | NDC | NDC to Respond
|  | NBPKSA | National Bank Pakistan KSA
Temenos
| Category | Deliverable
Technical Decision
Business Decision
Need Further discussion
| Level | As Per SMB
GAP Identified
| Process Discussion Started | Not Started
In Progress
Completed
Deffered