## Read Me
Definitions - Different Sheets used in Business Process Review
Products | It demonstrates model bank products being covered in BPR sheet and update bank product list if required
Processes | All Model Bank Processes relevant to bank business are mentioned and discussed with the bank
Scoping Gaps | This sheet contains Gaps, Back to core items – Customization that could be replaced by R20 core features, Existing customizations that will be retrofitted to R21 etc.
Follow Up Sheet | Items require follow up are recorded in this sheet for any action and decision to reflect in scoping gap sheet

## Version History
S.No | Version No | Created by | Creation Date | Amendment Date | Amended By | Amendment Reason | Amendment Description
1 | 1 | Salman Gill | 2021-12-19
2
3
Note: If there are any amendments to be made in the BPR sheet then please change the version name to 1.1 and so on. Amendment details should be properly given. If possible should be highlighted with different color.

## Sign Off
FIT & GAP APPROVAL SHEET
Customer Information File (CIF)
# | Name | Role | Company | Signature | Date
1 | Salman Arif

## Products
Product ID | PRODUCT | OVERVIEW | FEATURES | CURRENCY | INTEREST RATE | PA | Start Slippage | Duration Slippage | Process Discussion Status | Comments
Customer | Individual Customer | Functionality to open the Individual Customer. | Separate sectors for Individual Customers and its sub classifications. Capturing the details of the Customer at Branch level and profiling the details at CPU level. | NA | NA | NA |  |  | Completed
| Corpoarate Customer | Functionality to open Corporate Customer. | Separate sectors for Corporate Customers and its sub classifications. Capturing the details of the Customer at Branch level and profiling the details at CPU level. | NA | NA | NA |  |  | Completed
| Prospect Customer | Functionality to open Prospect Customer. | To open the Prospect Customer and its activation. | NA | NA | NA |  |  | Completed
Guarantees
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Start Slippage = IF([INTEREST RATE]="","",IF([FEATURES]<[INTEREST RATE],NETWORKDAYS([FEATURES]+2,[INTEREST RATE]+2,6)-1,0))
Duration Slippage = IF([PA]="","",IF([CURRENCY]<[PA],NETWORKDAYS([CURRENCY]+2,[PA]+2,6)-1,0))

## Processes
Process ID | Process Name | Level | Plan Start Date | Plan Finish Date | Duration (Hrs) | Actual Start Date | Actual Finish Date | Start Slippage | Duration Slippage | Process Discussion Status | Comments
WS01-CU | CUSTOMER
Customer Creation
WS01-CU-01 | Individual Customer | GAP Identified | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-02 | Corporate Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-03 | Create Prospect | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-04 | Activate Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-05 | Deceased Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-06 | Unauthorised Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-07 | Authorise/Delete Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-08 | Input Travel Notification | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-09 | Amend Active Travel Notification | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-10 | Authorise Travel Notification | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-11 | List Travel Notifications | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-12 | Capture Customer Segmentation Details | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
Amend & View Customer
WS01-CU-14 | Amend Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-15 | Authorize/Delete Amend Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-16 | Customer Addresses and Preferences | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-17 | Customer Delivery Preferences | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-18 | Customer Delivery Products | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-19 | Customer Address History | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-20 | Additional Address of Customer | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-21 | Set/Remove Posting Restrict | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-22 | Authorise/Delete Posting Restrict | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-23 | CUSTOMER.MASS.BLOCK,MASS.UNBLOCK | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-24 | Authorise / Delete Mass Block | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-25 | Amend / Reverse Mass Block | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-26 | Unblock Customer / Account | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-27 | Unblock Mass Block | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-28 | Unblock Bundle Arrangement | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
KYC
WS01-CU-24 | Create KYC | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-25 | KYC Details | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-26 | Risk Analysis | As Per SMB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
Enquiries
WS01-CU-27 | Customer Details | As Per MB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-28 | Customer List | As Per MB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-29 | Prospect Search | As Per MB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed
WS01-CU-30 | Customer Address History | As Per MB | 2021-12-19 | 2021-12-19 |  | 2021-12-19 | 2021-12-19 |  |  | Completed

## Scoping Gaps
Business Process Review Sheet - CUSTOMER
WS Ref | Description | Process Reference # | Gap Number | Process Name | Contact person | Raised by (Department) | MoSCoW Classification | Gap Category | Gap Type | Requirement Type | Gap Effort | Gap Status | Actions/ Comments | Functional / high Level Solution | Workshop Date | Man Days (Estimate) | Impact (Cost) | Impact (Time) | Man Days (New Estimate) | Dropped In | Dropped Date | NDC Comments | Enquiry/SMS/Email/Report
WS01-CU | Need to incorporate the mother name field in Individual Customer screen | WS01-CU-01.1 | WS01-CU-01 | Individual Customer |  |  | SHOULD Have | Bank Requirement | Configuration | New Requirement | Low | Agreed |  | Need to create the new LT with name of "Mother Name" and incorporate in LRT of Customer | 2021-12-19
[20 empty] | BPR | 2020-03-31
[20 empty] | BPR | 2020-03-31
[20 empty] | BPR | 2020-04-11
In case of any validation is required on KYC field from bank side after review then Gap type & Gap effort will be update accordingly.
Note on B34: admin: Details are required about KPK & GB for NTN length.

## Followup Sheet
S. No. | Date Raised | Gap Reference | Process Reference | Task Description | Priority | Status | Responsibility | Person To be Contacted | Category | Expected End Date | Last Modified Date | Next Followup Date | Actual End Date | Action / Comments | Aging | TAT
1 | 2021-12-19 | WS01-CU-01.1 | WS01-CU-01 | WS01-CU-05 | In Individual Customer Mother field required by bank | Low | NDC | Client | Core Retail Team | Deliverable

## Legend
Description of Drop Down Fields - Scoping Gap Sheet
Description
| Gap Category | Not Defined Yet | Category is to be identified
|  | Regulatory | As per regulations
|  | Bank Requirement | Specific to bank internal process or User Wishlist
|  | Sharia | It is based on sharia compliant
|  | PKMB | Pakistan Model Bank
| Gap Type | Configuration | Can be addressed through enquiry, versions, composite screens etc
|  | Parameterisation | Can be addressed through enquiry, versions, composite screens etc
|  | Customization | Development required
| MoSCoW | MUST Have
SHOULD Have
COULD Have
WON'T Have
| Requirement Type | Existing - Manual | Currently being addressed as a manual process
|  | Existing - System | Currently it is available in bank existing system
|  | New Requirement | It is a new requirement , can be bank specific, regulatory, sharia etc.
| Gap Effort | Low | 1-3 Days
|  | Medium | 3-10 Days
|  | High | > 10 Days
| Gap Status | Open | Decision to be made
|  | Dropped | Functionality not required
|  | Agreed | Gap has been accepted
|  | Workaround | The Workaround or Standard Model Bank Process has been accepted by the users
Description of Drop Down Fields - Scoping Gap Sheet
| Priority | Low | Does not impact on sign off
|  | Medium | Important but can be addressed in BRD
|  | High | Must be addressed to close and sign off BPR sheet
| Status | Open | Item still under follow up, action to be taken
|  | Closed | Requirement provided, decision has been made
| Responsibility | Client | Client to Respond
|  | NDC | NDC to Respond
|  | Anabatic | Other stakeholder to respond, Like Temenos, 3rd Party client etc
Temenos
| Category | Deliverable
Technical Decision
Business Decision
Need Further discussion
| Level | As Per SMB
GAP Identified
| Process Discussion Started | Not Started
In Progress
Completed
Deffered